## Read Me
Field Service to Project Operations Transition Plan
Companion workbook to the Managed ERP Services article on the February 28, 2027 deprecation. Prepared September 28, 2026.
What this is | A rough, editable plan to move from the legacy Dynamics 365 Field Service integration with finance and operations to the Field Service and Project Operations integration before Microsoft's February 28, 2027 end date. It is a reference plan for a medium-complexity scope starting October 5, 2026 with go-live on February 8, 2027.
Sheets | Settings: status date, key dates, holidays. WBS Plan: 85 tasks and 8 workstream summaries with a weekly Gantt. Workstreams: roll-up by workstream. Gates: G1-G5 and go-live with exit criteria. Estimator: complexity matrix and calculator. Self-Check: 12-question readiness score. RAID: risks, assumptions, issues, dependencies.
How to use it | 1) Set the as-of date on Settings each week. 2) Use the Estimator to find your complexity cell; shift planned dates on WBS Plan if your cell is not medium/medium. 3) Fill 'Assigned to' for every task. 4) Each week update Status, % complete and Actual finish. 5) Review the Schedule flag, Workstreams roll-up and Gates at steering.
Cell legend | Yellow fill = cells you update. Blue text = planned inputs you may change (dates, estimates). Black text = formulas; do not overwrite. Green text = values pulled from another sheet.
Schedule flags | On plan: not yet due. Start due: start date reached with 0% complete. Overdue: finish date passed and not complete. Past deadline: planned finish after February 28, 2027 (hypercare tasks excepted). Done: status is Complete.
Example update | Task 1.1 'Mobilize program' on Oct 7: Status = Complete, % complete = 100%, Actual finish = 07-Oct-26. Its flag turns to Done and WS1 progress rises.
MS Project / Smartsheet | Columns A-N import cleanly: Task ID, WBS, Level (outline), Task name, Start, Finish, Predecessors (Task IDs), Owner (resource). Predecessors are finish-to-start by default; adjust overlaps after import.
Key Microsoft sources | Feature deprecations: learn.microsoft.com/en-us/dynamics365/field-service/deprecations-field-service ¦ Integration overview: learn.microsoft.com/en-us/dynamics365/field-service/project-operations-integration ¦ Setup guide: learn.microsoft.com/en-us/dynamics365/field-service/project-operations-integration-setup (all checked September 28, 2026).
Caveats | Durations, thresholds and effort shares are estimates for mid-market organizations, not Microsoft guidance or a quote. Validate licensing with your licensing advisor.
Contact | Managed ERP Services, Houston, TX ¦ start@managederpservices.com ¦ +1-832-449-1520

## Settings
Plan Settings
Change the yellow cells; every date-driven formula in the workbook reads from this sheet.
Setting | Value | Note
As-of date (status date) | 2026-09-28 | Replace with =TODAY() to keep flags live, or set to your weekly status date.
Program start (Monday) | 2026-10-05 | Reference plan start. Planned task dates on 'WBS Plan' are entered, not derived.
Target go-live | 2027-02-08 | Monday after the Feb 6-7 cutover weekend.
Hypercare exit | 2027-02-26 | Gate G5.
Microsoft end date for legacy FS-F&O integration | 2027-02-28 | Source: learn.microsoft.com/en-us/dynamics365/field-service/deprecations-field-service (checked Sep 28, 2026).
Holiday freeze start | 2026-12-21 | No build or test work planned.
Holiday freeze end | 2027-01-01
Calendar days from as-of date to Microsoft end date | 153
Calendar days of buffer between go-live and end date | 20
Working days from program start to go-live (net of holidays) | 79
Non-working days (used by NETWORKDAYS)
Date | Reason
2026-11-26 | Thanksgiving
2026-11-27 | Day after Thanksgiving
2026-12-21 | Holiday freeze
2026-12-22 | Holiday freeze
2026-12-23 | Holiday freeze
2026-12-24 | Holiday freeze
2026-12-25 | Holiday freeze
2026-12-28 | Holiday freeze
2026-12-29 | Holiday freeze
2026-12-30 | Holiday freeze
2026-12-31 | Holiday freeze
2027-01-01 | Holiday freeze
Add company holidays (e.g., MLK Day Jan 18, Presidents' Day Feb 15) in B20:B40 if you observe them.

## WBS Plan
Field Service to Project Operations Transition - Work Breakdown Structure
Reference plan for a medium-complexity scope. Edit yellow columns weekly; grey-headed columns are formulas.
| As of | 2026-09-28 |  | Go-live | 2027-02-08 |  | Microsoft end date |  | 2027-02-28 | Freeze | 2026-12-21 | 2027-01-01 |  | Overall % complete |  | 0%
| Legend: | Yellow = you update |  | Blue text = planned input |  |  | Black = formula |  | Gantt: blue task, navy summary, orange milestone; grey header = holiday freeze; red header = end-date week
[20 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22
Task ID | WBS | Level | Workstream | Phase | Task / Deliverable | Type | Owner (role) | Assigned to | Planned start | Planned finish | Working days | Predecessors (Task ID) | Predecessors (WBS) | Status | % complete | Actual finish | Schedule flag | Exit criteria / deliverable | Notes / risks | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01
1 | 1 | 1 | WS1 Program Management & Governance | All | WS1 Program Management & Governance | Summary |  |  | 2026-10-05 | 2027-02-26 | 119 |  |  | Not started | 0% |  | On plan | bar: 2026-10-05 to 2027-02-22
2 | 1.1 | 2 | WS1 Program Management & Governance | Assess | Mobilize program: confirm sponsor, program owner and budget envelope | Task | Sponsor / Program Manager |  | 2026-10-05 | 2026-10-07 | 3 |  |  | Not started | 0% |  | On plan | Program charter; sponsor and owner named | bar: 2026-10-05
3 | 1.2 | 2 | WS1 Program Management & Governance | Assess | Stand up governance: weekly steering, RAID log, decision log, 48-hour decision rule | Task | Program Manager |  | 2026-10-05 | 2026-10-09 | 5 | 2 | 1.1 | Not started | 0% |  | On plan | Governance cadence and logs live | bar: 2026-10-05
4 | 1.3 | 2 | WS1 Program Management & Governance | Assess | Build integrated plan and budget baseline | Task | Program Manager |  | 2026-10-12 | 2026-10-21 | 8 | 3 | 1.2 | Not started | 0% |  | On plan | Baselined plan and budget | bar: 2026-10-12 to 2026-10-19
5 | 1.4 | 2 | WS1 Program Management & Governance | Assess | Secure delivery team / partner through March 2027 | Task | Sponsor / Program Manager |  | 2026-10-05 | 2026-10-16 | 10 | 2 | 1.1 | Not started | 0% |  | On plan | Signed SOW or resource plan | bar: 2026-10-05 to 2026-10-12
6 | 1.5 | 2 | WS1 Program Management & Governance | Assess | G1 - Scope agreed (assessment signed off) | Milestone | Sponsor |  | 2026-10-23 | 2026-10-23 | 0 | 18,31,4,5 | 2.5, 3.3, 1.3, 1.4 | Not started | 0% |  | On plan | Impact assessment, deployment model, must-do scope, budget approved | bar: 2026-10-19
7 | 1.6 | 2 | WS1 Program Management & Governance | Design | G2 - Design signed off | Milestone | Sponsor / Controller |  | 2026-11-13 | 2026-11-13 | 0 | 27,54,64 | 2.14, 5.2, 6.2 | Not started | 0% |  | On plan | Signed solution design, data mapping, cutover strategy | bar: 2026-11-09
8 | 1.7 | 2 | WS1 Program Management & Governance | Build | G3 - Build complete in sandbox | Milestone | Program Manager |  | 2026-12-18 | 2026-12-18 | 0 | 50,57 | 4.12, 5.5 | Not started | 0% |  | On plan | Integration enabled in sandbox; mock load 1 reconciled | bar: 2026-12-14
9 | 1.8 | 2 | WS1 Program Management & Governance | Test | G4 - Go / no-go decision | Milestone | Sponsor |  | 2027-02-03 | 2027-02-03 | 0 | 71,61,80,37 | 6.9, 5.9, 7.8, 3.9 | Not started | 0% |  | On plan | UAT signed; no open critical defects; users trained | bar: 2027-02-01
10 | 1.9 | 2 | WS1 Program Management & Governance | Hypercare | G5 - Live and stable (hypercare exit) | Milestone | Sponsor |  | 2027-02-26 | 2027-02-26 | 0 | 92 | 8.11 | Not started | 0% |  | On plan | Clean daily reconciliations; legacy removed | bar: 2027-02-22
11 | 1.10 | 2 | WS1 Program Management & Governance | All | Weekly status reporting and steering (recurring) | Task | Program Manager |  | 2026-10-12 | 2027-02-26 | 88 | 3 | 1.2 | Not started | 0% |  | On plan | Weekly status pack; decisions logged | bar: 2026-10-12 to 2027-02-22
12 | 1.11 | 2 | WS1 Program Management & Governance | Hypercare | Phase 2 backlog and lessons learned | Task | Program Manager |  | 2027-02-22 | 2027-02-26 | 5 | 90 | 8.9 | Not started | 0% |  | On plan | Prioritized Phase 2 backlog | bar: 2027-02-22
13 | 2 | 1 | WS2 Process & Solution Design | All | WS2 Process & Solution Design | Summary |  |  | 2026-10-07 | 2026-11-13 | 73 |  |  | Not started | 0% |  | On plan | bar: 2026-10-05 to 2026-11-09
14 | 2.1 | 2 | WS2 Process & Solution Design | Assess | Discovery workshops with service operations, project accounting and finance | Task | Solution Architect |  | 2026-10-07 | 2026-10-14 | 6 | 2 | 1.1 | Not started | 0% |  | On plan | Workshop notes and pain points | bar: 2026-10-05 to 2026-10-12
15 | 2.2 | 2 | WS2 Process & Solution Design | Assess | Document current-state work order to F&O posting flows | Task | Functional Consultant (F&O) |  | 2026-10-07 | 2026-10-16 | 8 | 2 | 1.1 | Not started | 0% |  | On plan | Current-state process map | bar: 2026-10-05 to 2026-10-12
16 | 2.3 | 2 | WS2 Process & Solution Design | Assess | Evaluate deployment models (FS + F&SCM vs FS + PO + F&SCM) | Task | Solution Architect |  | 2026-10-12 | 2026-10-20 | 7 | 14 | 2.1 | Not started | 0% |  | On plan | Deployment model recommendation | bar: 2026-10-12 to 2026-10-19
17 | 2.4 | 2 | WS2 Process & Solution Design | Assess | Define must-do vs Phase 2 scope (minimum viable transition) | Task | Solution Architect / Program Manager |  | 2026-10-16 | 2026-10-22 | 5 | 16,40 | 2.3, 4.2 | Not started | 0% |  | On plan | Scope statement | bar: 2026-10-12 to 2026-10-19
18 | 2.5 | 2 | WS2 Process & Solution Design | Assess | Impact assessment report | Task | Solution Architect |  | 2026-10-19 | 2026-10-22 | 4 | 17,40,53 | 2.4, 4.2, 5.1 | Not started | 0% |  | On plan | Impact assessment | bar: 2026-10-19
19 | 2.6 | 2 | WS2 Process & Solution Design | Design | Design: work order to project and contract line mapping | Task | Solution Architect |  | 2026-10-26 | 2026-10-30 | 5 | 6 | 1.5 | Not started | 0% |  | On plan | Mapping design | bar: 2026-10-26
20 | 2.7 | 2 | WS2 Process & Solution Design | Design | Design: project categories, cost and revenue, revenue recognition | Task | Functional Consultant (F&O) / Controller |  | 2026-10-26 | 2026-11-03 | 7 | 6 | 1.5 | Not started | 0% |  | On plan | Category and posting design | bar: 2026-10-26 to 2026-11-02
21 | 2.8 | 2 | WS2 Process & Solution Design | Design | Design: company and legal entity alignment | Task | Functional Consultant (F&O) |  | 2026-10-28 | 2026-11-03 | 5 | 6 | 1.5 | Not started | 0% |  | On plan | Legal entity mapping | bar: 2026-10-26 to 2026-11-02
22 | 2.9 | 2 | WS2 Process & Solution Design | Design | Decide price/cost source (Field Service vs Project Operations) and MUL auto-approval | Task | Controller / Solution Architect |  | 2026-11-02 | 2026-11-04 | 3 | 20 | 2.7 | Not started | 0% |  | On plan | Documented decision | bar: 2026-11-02
23 | 2.10 | 2 | WS2 Process & Solution Design | Design | Design time entry flow and approvals (Field Service to Project Operations) | Task | Functional Consultant (FS/PO) |  | 2026-11-02 | 2026-11-06 | 5 | 19 | 2.6 | Not started | 0% |  | On plan | Time approval design | bar: 2026-11-02
24 | 2.11 | 2 | WS2 Process & Solution Design | Design | Design inventory: stocked products, warehouses, serial/batch tracking | Task | Functional Consultant (SCM) |  | 2026-11-02 | 2026-11-06 | 5 | 19 | 2.6 | Not started | 0% |  | On plan | Inventory design | bar: 2026-11-02
25 | 2.12 | 2 | WS2 Process & Solution Design | Design | Open work order cutover strategy (close-out vs migrate) | Task | Solution Architect / Service Ops Lead |  | 2026-11-04 | 2026-11-10 | 5 | 19 | 2.6 | Not started | 0% |  | On plan | Cutover strategy | bar: 2026-11-02 to 2026-11-09
26 | 2.13 | 2 | WS2 Process & Solution Design | Design | Solution design document and configuration workbook | Task | Solution Architect |  | 2026-11-05 | 2026-11-12 | 6 | 22,23,24,25 | 2.9, 2.10, 2.11, 2.12 | Not started | 0% |  | On plan | Solution design; config workbook | bar: 2026-11-02 to 2026-11-09
27 | 2.14 | 2 | WS2 Process & Solution Design | Design | Design review and sign-off | Task | Sponsor / Controller / Service Ops Lead |  | 2026-11-12 | 2026-11-13 | 2 | 26 | 2.13 | Not started | 0% |  | On plan | Signed design | bar: 2026-11-09
28 | 3 | 1 | WS3 Environments, Licensing & Security | All | WS3 Environments, Licensing & Security | Summary |  |  | 2026-10-05 | 2027-01-29 | 61 |  |  | Not started | 0% |  | On plan | bar: 2026-10-05 to 2027-01-25
29 | 3.1 | 2 | WS3 Environments, Licensing & Security | Assess | Check Field Service (8.8.142.0+) and Project Operations (4.162.0.0+) versions in all environments | Task | Platform Admin |  | 2026-10-05 | 2026-10-07 | 3 |  |  | Not started | 0% |  | On plan | Version register | bar: 2026-10-05
30 | 3.2 | 2 | WS3 Environments, Licensing & Security | Assess | Protect current sandbox; agree environment strategy (build, test, UAT, legacy support) | Task | Platform Admin |  | 2026-10-07 | 2026-10-09 | 3 | 29 | 3.1 | Not started | 0% |  | On plan | Environment plan | bar: 2026-10-05
31 | 3.3 | 2 | WS3 Environments, Licensing & Security | Assess | Confirm licensing: Project Operations for installing user; Power Automate for recurring flow | Task | Platform Admin / Licensing Advisor |  | 2026-10-12 | 2026-10-16 | 5 | 16 | 2.3 | Not started | 0% |  | On plan | License requirement list | bar: 2026-10-12
32 | 3.4 | 2 | WS3 Environments, Licensing & Security | Design | Procure licenses | Task | Platform Admin / Procurement |  | 2026-10-19 | 2026-11-06 | 15 | 31 | 3.3 | Not started | 0% |  | On plan | Licenses assigned | bar: 2026-10-19 to 2026-11-02
33 | 3.5 | 2 | WS3 Environments, Licensing & Security | Design | Copy production to build sandbox (F&O and linked Dataverse) | Task | Platform Admin |  | 2026-10-26 | 2026-11-06 | 10 | 30 | 3.2 | Not started | 0% |  | On plan | Build sandbox ready | bar: 2026-10-26 to 2026-11-02
34 | 3.6 | 2 | WS3 Environments, Licensing & Security | Build | Upgrade Field Service and install/upgrade Project Operations in build sandbox | Task | Platform Admin |  | 2026-11-09 | 2026-11-13 | 5 | 33,32 | 3.5, 3.4 | Not started | 0% |  | On plan | Sandbox on required versions | bar: 2026-11-09
35 | 3.7 | 2 | WS3 Environments, Licensing & Security | Build | Security roles and integration flow owner account | Task | Platform Admin |  | 2026-11-09 | 2026-11-20 | 10 | 32 | 3.4 | Not started | 0% |  | On plan | Security matrix | bar: 2026-11-09 to 2026-11-16
36 | 3.8 | 2 | WS3 Environments, Licensing & Security | Build | Prepare UAT environment (refresh from production, apply build) | Task | Platform Admin |  | 2026-12-14 | 2026-12-18 | 5 | 34 | 3.6 | Not started | 0% |  | On plan | UAT environment ready | bar: 2026-12-14
37 | 3.9 | 2 | WS3 Environments, Licensing & Security | Cutover | Production readiness: versions, licenses, roles, flow owner | Task | Platform Admin |  | 2027-01-25 | 2027-01-29 | 5 | 35 | 3.7 | Not started | 0% |  | On plan | Production readiness checklist | bar: 2027-01-25
38 | 4 | 1 | WS4 Integration & Technical Build | All | WS4 Integration & Technical Build | Summary |  |  | 2026-10-07 | 2027-01-29 | 95 |  |  | Not started | 0% |  | On plan | bar: 2026-10-05 to 2027-01-25
39 | 4.1 | 2 | WS4 Integration & Technical Build | Assess | Technical inventory: dual-write maps, plugins, flows, scripts, ISVs, integrations, reports | Task | Technical Lead |  | 2026-10-07 | 2026-10-16 | 8 | 29 | 3.1 | Not started | 0% |  | On plan | Technical inventory | bar: 2026-10-05 to 2026-10-12
40 | 4.2 | 2 | WS4 Integration & Technical Build | Assess | Size each customization: keep, refactor or retire | Task | Technical Lead |  | 2026-10-16 | 2026-10-21 | 4 | 39 | 4.1 | Not started | 0% |  | On plan | Refactor estimate | bar: 2026-10-12 to 2026-10-19
41 | 4.3 | 2 | WS4 Integration & Technical Build | Build | Install Project Operations dual-write map versions; activate manage stocked products | Task | Technical Lead |  | 2026-11-16 | 2026-11-18 | 3 | 34,7 | 3.6, 1.6 | Not started | 0% |  | On plan | Maps running in sandbox | bar: 2026-11-16
42 | 4.4 | 2 | WS4 Integration & Technical Build | Build | Enable virtual entity ProjInventOnHandEntity | Task | Technical Lead |  | 2026-11-16 | 2026-11-17 | 2 | 34 | 3.6 | Not started | 0% |  | On plan | Virtual entity enabled | bar: 2026-11-16
43 | 4.5 | 2 | WS4 Integration & Technical Build | Build | Uninstall legacy in build sandbox; install FS-PO integration package; enable toggle | Task | Technical Lead |  | 2026-11-18 | 2026-11-20 | 3 | 41,42 | 4.3, 4.4 | Not started | 0% |  | On plan | New integration enabled in sandbox | bar: 2026-11-16
44 | 4.6 | 2 | WS4 Integration & Technical Build | Build | Configure integration settings (auto-approve, price/cost source) | Task | Functional Consultant (FS/PO) |  | 2026-11-19 | 2026-11-20 | 2 | 43,22 | 4.5, 2.9 | Not started | 0% |  | On plan | Settings configured | bar: 2026-11-16
45 | 4.7 | 2 | WS4 Integration & Technical Build | Build | Configure projects, contracts, categories and price lists per design | Task | Functional Consultant (FS/PO) |  | 2026-11-23 | 2026-12-04 | 8 | 44 | 4.6 | Not started | 0% |  | On plan | Configured sandbox | bar: 2026-11-23 to 2026-11-30
46 | 4.8 | 2 | WS4 Integration & Technical Build | Build | Refactor plugins, flows and scripts on work order transactions | Task | Developer |  | 2026-11-23 | 2026-12-11 | 13 | 43,40 | 4.5, 4.2 | Not started | 0% |  | On plan | Refactored code | bar: 2026-11-23 to 2026-12-07
47 | 4.9 | 2 | WS4 Integration & Technical Build | Build | Update downstream integrations (billing, payroll, portals) | Task | Developer |  | 2026-11-30 | 2026-12-11 | 10 | 46 | 4.8 | Not started | 0% |  | On plan | Updated integrations | bar: 2026-11-30 to 2026-12-07
48 | 4.10 | 2 | WS4 Integration & Technical Build | Build | Rebuild critical reports (billing, work in progress, margin) | Task | BI Developer |  | 2026-11-30 | 2026-12-16 | 13 | 45 | 4.7 | Not started | 0% |  | On plan | Critical reports rebuilt | bar: 2026-11-30 to 2026-12-14
49 | 4.11 | 2 | WS4 Integration & Technical Build | Build | Review mobile offline profiles installed by the integration | Task | Functional Consultant (FS/PO) |  | 2026-12-07 | 2026-12-10 | 4 | 43 | 4.5 | Not started | 0% |  | On plan | Offline profile decision | bar: 2026-12-07
50 | 4.12 | 2 | WS4 Integration & Technical Build | Build | Unit test and package solutions (ALM) | Task | Technical Lead |  | 2026-12-14 | 2026-12-18 | 5 | 46,47,48,49 | 4.8, 4.9, 4.10, 4.11 | Not started | 0% |  | On plan | Deployable solution packages | bar: 2026-12-14
51 | 4.13 | 2 | WS4 Integration & Technical Build | Test | Defect fixing during SIT and UAT | Task | Developer |  | 2027-01-04 | 2027-01-29 | 20 | 50 | 4.12 | Not started | 0% |  | On plan | Defects closed | bar: 2027-01-04 to 2027-01-25
52 | 5 | 1 | WS5 Data Migration & Reconciliation | All | WS5 Data Migration & Reconciliation | Summary |  |  | 2026-10-12 | 2027-02-04 | 76 |  |  | Not started | 0% |  | On plan | bar: 2026-10-12 to 2027-02-01
53 | 5.1 | 2 | WS5 Data Migration & Reconciliation | Assess | Data profiling: open work orders, projects, categories, products, service accounts | Task | Data Lead |  | 2026-10-12 | 2026-10-21 | 8 | 2 | 1.1 | Not started | 0% |  | On plan | Data profile and volumes | bar: 2026-10-12 to 2026-10-19
54 | 5.2 | 2 | WS5 Data Migration & Reconciliation | Design | Data mapping specification (legacy subprojects to projects and contract lines) | Task | Data Lead / Functional Consultant (F&O) |  | 2026-11-02 | 2026-11-13 | 10 | 19,20 | 2.6, 2.7 | Not started | 0% |  | On plan | Mapping specification | bar: 2026-11-02 to 2026-11-09
55 | 5.3 | 2 | WS5 Data Migration & Reconciliation | Build | Master data cleansing (duplicates, missing categories, units of measure) | Task | Data Lead / Business Data Owners |  | 2026-11-16 | 2026-12-11 | 18 | 54 | 5.2 | Not started | 0% |  | On plan | Cleansed master data | bar: 2026-11-16 to 2026-12-07
56 | 5.4 | 2 | WS5 Data Migration & Reconciliation | Build | Build load templates and scripts | Task | Data Lead |  | 2026-11-30 | 2026-12-04 | 5 | 54 | 5.2 | Not started | 0% |  | On plan | Load templates | bar: 2026-11-30
57 | 5.5 | 2 | WS5 Data Migration & Reconciliation | Build | Mock load 1 and reconciliation | Task | Data Lead / Finance |  | 2026-12-07 | 2026-12-11 | 5 | 56,45 | 5.4, 4.7 | Not started | 0% |  | On plan | Mock 1 reconciliation | bar: 2026-12-07
58 | 5.6 | 2 | WS5 Data Migration & Reconciliation | Test | Mock load 2 (UAT data) and reconciliation | Task | Data Lead / Finance |  | 2027-01-04 | 2027-01-08 | 5 | 57,36 | 5.5, 3.8 | Not started | 0% |  | On plan | Mock 2 reconciliation | bar: 2027-01-04
59 | 5.7 | 2 | WS5 Data Migration & Reconciliation | Test | Open work order close-out campaign | Task | Service Ops Lead |  | 2027-01-11 | 2027-02-04 | 19 | 25 | 2.12 | Not started | 0% |  | On plan | Open work order count at target | bar: 2027-01-11 to 2027-02-01
60 | 5.8 | 2 | WS5 Data Migration & Reconciliation | Test | Mock load 3 / dress rehearsal with cutover timings | Task | Data Lead |  | 2027-01-25 | 2027-01-28 | 4 | 58 | 5.6 | Not started | 0% |  | On plan | Timed rehearsal results | bar: 2027-01-25
61 | 5.9 | 2 | WS5 Data Migration & Reconciliation | Test | Reconciliation sign-off by finance | Task | Controller |  | 2027-01-28 | 2027-01-29 | 2 | 60 | 5.8 | Not started | 0% |  | On plan | Signed reconciliation | bar: 2027-01-25
62 | 6 | 1 | WS6 Testing & Quality | All | WS6 Testing & Quality | Summary |  |  | 2026-10-26 | 2027-02-02 | 70 |  |  | Not started | 0% |  | On plan | bar: 2026-10-26 to 2027-02-01
63 | 6.1 | 2 | WS6 Testing & Quality | Design | Book named business testers (dispatch, field, project accounting, finance) | Task | Test Lead / Program Manager |  | 2026-10-26 | 2026-11-06 | 10 | 6 | 1.5 | Not started | 0% |  | On plan | Tester roster for Jan 18-29 | bar: 2026-10-26 to 2026-11-02
64 | 6.2 | 2 | WS6 Testing & Quality | Design | Test strategy and GL-posting scenario list (10-15 scenarios) | Task | Test Lead |  | 2026-11-09 | 2026-11-13 | 5 | 26 | 2.13 | Not started | 0% |  | On plan | Test strategy | bar: 2026-11-09
65 | 6.3 | 2 | WS6 Testing & Quality | Build | Write end-to-end test scripts (work order to MUL to actuals to journal to invoice) | Task | Test Lead |  | 2026-11-16 | 2026-12-11 | 18 | 64 | 6.2 | Not started | 0% |  | On plan | Test scripts | bar: 2026-11-16 to 2026-12-07
66 | 6.4 | 2 | WS6 Testing & Quality | Test | System integration testing (SIT) | Task | Test Lead |  | 2027-01-04 | 2027-01-15 | 10 | 50,58 | 4.12, 5.6 | Not started | 0% |  | On plan | SIT results | bar: 2027-01-04 to 2027-01-11
67 | 6.5 | 2 | WS6 Testing & Quality | Test | F&O regression testing (billing, inventory, month-end) | Task | Functional Consultant (F&O) |  | 2027-01-11 | 2027-01-15 | 5 | 66 | 6.4 | Not started | 0% |  | On plan | Regression results | bar: 2027-01-11
68 | 6.6 | 2 | WS6 Testing & Quality | Test | Mobile offline sync testing on real devices | Task | Functional Consultant (FS/PO) |  | 2027-01-11 | 2027-01-15 | 5 | 49 | 4.11 | Not started | 0% |  | On plan | Device test log | bar: 2027-01-11
69 | 6.7 | 2 | WS6 Testing & Quality | Test | User acceptance testing (UAT) | Task | Business Testers |  | 2027-01-18 | 2027-01-27 | 8 | 66,63 | 6.4, 6.1 | Not started | 0% |  | On plan | UAT evidence | bar: 2027-01-18 to 2027-01-25
70 | 6.8 | 2 | WS6 Testing & Quality | Test | Cutover rehearsal in sandbox (uninstall legacy, enable new, load, reconcile) | Task | Cutover Manager |  | 2027-01-25 | 2027-01-29 | 5 | 82 | 8.1 | Not started | 0% |  | On plan | Rehearsal report | bar: 2027-01-25
71 | 6.9 | 2 | WS6 Testing & Quality | Test | UAT sign-off and go/no-go pack | Task | Test Lead / Sponsor |  | 2027-01-28 | 2027-02-02 | 4 | 69,70 | 6.7, 6.8 | Not started | 0% |  | On plan | Signed UAT; go/no-go pack | bar: 2027-01-25 to 2027-02-01
72 | 7 | 1 | WS7 Training & Change Management | All | WS7 Training & Change Management | Summary |  |  | 2026-11-16 | 2027-02-05 | 79 |  |  | Not started | 0% |  | On plan | bar: 2026-11-16 to 2027-02-01
73 | 7.1 | 2 | WS7 Training & Change Management | Design | Stakeholder and impact analysis by role | Task | Change Lead |  | 2026-11-16 | 2026-11-20 | 5 | 7 | 1.6 | Not started | 0% |  | On plan | Role impact matrix | bar: 2026-11-16
74 | 7.2 | 2 | WS7 Training & Change Management | Design | Communications plan and announcements | Task | Change Lead |  | 2026-11-16 | 2026-11-25 | 8 | 73 | 7.1 | Not started | 0% |  | On plan | Comms plan | bar: 2026-11-16 to 2026-11-23
75 | 7.3 | 2 | WS7 Training & Change Management | Build | Identify and onboard super users | Task | Change Lead |  | 2026-11-30 | 2026-12-11 | 10 | 73 | 7.1 | Not started | 0% |  | On plan | Super user network | bar: 2026-11-30 to 2026-12-07
76 | 7.4 | 2 | WS7 Training & Change Management | Build | Build role-based training materials and quick-reference cards | Task | Change Lead / Functional Consultants |  | 2026-12-07 | 2027-01-08 | 15 | 45 | 4.7 | Not started | 0% |  | On plan | Training materials | bar: 2026-12-07 to 2027-01-04
77 | 7.5 | 2 | WS7 Training & Change Management | Test | Update standard operating procedures (dispatch, time approval, project accounting, month-end) | Task | Process Owners |  | 2027-01-04 | 2027-01-15 | 10 | 76 | 7.4 | Not started | 0% |  | On plan | Updated SOPs | bar: 2027-01-04 to 2027-01-11
78 | 7.6 | 2 | WS7 Training & Change Management | Train | Deliver role-based training (dispatch, project accounting, finance) | Task | Change Lead / Super Users |  | 2027-01-11 | 2027-02-03 | 18 | 76 | 7.4 | Not started | 0% |  | On plan | Attendance log | bar: 2027-01-11 to 2027-02-01
79 | 7.7 | 2 | WS7 Training & Change Management | Train | Technician briefing (offline sync, time entry) | Task | Service Ops Lead |  | 2027-01-25 | 2027-02-05 | 10 | 68 | 6.6 | Not started | 0% |  | On plan | Briefing complete | bar: 2027-01-25 to 2027-02-01
80 | 7.8 | 2 | WS7 Training & Change Management | Train | Readiness check (ADKAR pulse survey) | Task | Change Lead |  | 2027-02-01 | 2027-02-03 | 3 | 78 | 7.6 | Not started | 0% |  | On plan | Readiness results | bar: 2027-02-01
81 | 8 | 1 | WS8 Cutover, Hypercare & Decommission | All | WS8 Cutover, Hypercare & Decommission | Summary |  |  | 2027-01-18 | 2027-03-05 | 42 |  |  | Not started | 0% |  | On plan | bar: 2027-01-18 to 2027-03-01
82 | 8.1 | 2 | WS8 Cutover, Hypercare & Decommission | Test | Draft hour-by-hour cutover runbook | Task | Cutover Manager |  | 2027-01-18 | 2027-01-22 | 5 | 25 | 2.12 | Not started | 0% |  | On plan | Draft runbook | bar: 2027-01-18
83 | 8.2 | 2 | WS8 Cutover, Hypercare & Decommission | Test | Finalize runbook timings after rehearsal | Task | Cutover Manager |  | 2027-01-28 | 2027-02-01 | 3 | 70 | 6.8 | Not started | 0% |  | On plan | Final runbook | bar: 2027-01-25 to 2027-02-01
84 | 8.3 | 2 | WS8 Cutover, Hypercare & Decommission | Cutover | Communicate transaction freeze and cutover schedule | Task | Change Lead |  | 2027-02-01 | 2027-02-03 | 3 | 83 | 8.2 | Not started | 0% |  | On plan | Cutover notice sent | bar: 2027-02-01
85 | 8.4 | 2 | WS8 Cutover, Hypercare & Decommission | Cutover | Transaction freeze; final postings on legacy path | Task | Cutover Manager / Finance |  | 2027-02-04 | 2027-02-05 | 2 | 9 | 1.8 | Not started | 0% |  | On plan | Legacy postings complete | bar: 2027-02-01
86 | 8.5 | 2 | WS8 Cutover, Hypercare & Decommission | Cutover | Uninstall legacy integration in production | Task | Technical Lead |  | 2027-02-06 | 2027-02-06 | 0 | 85 | 8.4 | Not started | 0% |  | On plan | Legacy uninstalled | bar: 2027-02-01
87 | 8.6 | 2 | WS8 Cutover, Hypercare & Decommission | Cutover | Install and enable new integration in production; load open work orders | Task | Technical Lead / Data Lead |  | 2027-02-06 | 2027-02-07 | 0 | 86 | 8.5 | Not started | 0% |  | On plan | New integration live | bar: 2027-02-01
88 | 8.7 | 2 | WS8 Cutover, Hypercare & Decommission | Cutover | Smoke test and reconcile first postings | Task | Test Lead / Finance |  | 2027-02-07 | 2027-02-08 | 1 | 87 | 8.6 | Not started | 0% |  | On plan | Smoke test passed | bar: 2027-02-01 to 2027-02-08
89 | 8.8 | 2 | WS8 Cutover, Hypercare & Decommission | Cutover | Go-live | Milestone | Sponsor |  | 2027-02-08 | 2027-02-08 | 0 | 88 | 8.7 | Not started | 0% |  | On plan | Go-live confirmed | bar: 2027-02-08
90 | 8.9 | 2 | WS8 Cutover, Hypercare & Decommission | Hypercare | Hypercare: daily reconciliation and defect triage | Task | Cutover Manager / Support Team |  | 2027-02-08 | 2027-02-26 | 15 | 89 | 8.8 | Not started | 0% |  | On plan | Daily reconciliation log | bar: 2027-02-08 to 2027-02-22
91 | 8.10 | 2 | WS8 Cutover, Hypercare & Decommission | Hypercare | Decommission legacy components (solutions, maps, jobs) | Task | Technical Lead |  | 2027-02-15 | 2027-02-19 | 5 | 89 | 8.8 | Not started | 0% |  | On plan | Legacy removed | bar: 2027-02-15
92 | 8.11 | 2 | WS8 Cutover, Hypercare & Decommission | Hypercare | Hypercare exit report | Task | Cutover Manager |  | 2027-02-24 | 2027-02-26 | 3 | 90 | 8.9 | Not started | 0% |  | On plan | Exit report | bar: 2027-02-22
93 | 8.12 | 2 | WS8 Cutover, Hypercare & Decommission | Hypercare | Support February month-end close (first close on new path) | Task | Support Team / Finance |  | 2027-03-01 | 2027-03-05 | 5 | 90 | 8.9 | Not started | 0% |  | On plan | February close completed | bar: 2027-03-01

## Workstreams
Workstream Roll-up
Counts, weighted progress and dates roll up from 'WBS Plan'. Effort share is an indicative input.
Workstream | Purpose | Typical owner | Key outputs | Indicative effort share | Tasks | Complete | Weighted % complete | Planned start | Planned finish | Overdue tasks | Past-deadline tasks
WS1 Program Management & Governance | Keep scope, time, cost and decisions under control | Client program manager with partner PM | Integrated plan, weekly status, decision log | 10% | 11 | 0 | 0% | 2026-10-05 | 2027-02-26 | 0 | 0
WS2 Process & Solution Design | Decide how service work becomes project financials | Solution architect with service ops, project accounting, controller | Signed solution design, configuration workbook | 15% | 14 | 0 | 0% | 2026-10-07 | 2026-11-13 | 0 | 0
WS3 Environments, Licensing & Security | Make sure the platform is ready and licensed | IT platform administrator | Ready environments, license confirmation, security matrix | 5% | 9 | 0 | 0% | 2026-10-05 | 2027-01-29 | 0 | 0
WS4 Integration & Technical Build | Build the new path and fix what depended on the old one | Technical lead and developers | Configured solution, deployable packages, rebuilt reports | 25% | 13 | 0 | 0% | 2026-10-07 | 2027-01-29 | 0 | 0
WS5 Data Migration & Reconciliation | Move only the data that must move, and prove it balances | Data lead with finance | Load templates, reconciliation sign-off | 15% | 9 | 0 | 0% | 2026-10-12 | 2027-02-04 | 0 | 0
WS6 Testing & Quality | Prove the money flows correctly before go-live | Test lead with named business testers | Test evidence, defect log, UAT sign-off | 15% | 9 | 0 | 0% | 2026-10-26 | 2027-02-02 | 0 | 0
WS7 Training & Change Management | Get each role ready for the change it will see | Change lead with super users | Training materials, readiness results, comms plan | 8% | 8 | 0 | 0% | 2026-11-16 | 2027-02-05 | 0 | 0
WS8 Cutover, Hypercare & Decommission | Switch safely and leave nothing of the legacy path behind | Cutover manager | Runbook, go-live sign-off, hypercare exit report | 7% | 12 | 0 | 0% | 2027-01-18 | 2027-03-05 | 0 | 0
Total |  |  |  | 100% | 85 | 0 | 0% | 2026-10-05 | 2027-03-05 | 0 | 0
Effort share is an indicative split for a mid-market program, not a quote; adjust to your assessment.
Formulas:
Planned start = MINIFS('WBS Plan'!$J7:J99,'WBS Plan'!$D7:D99,[Workstream],'WBS Plan'!$G7:G99,"<>Summary")
Planned start = MIN(J5:[Planned start, row above])
Planned finish = MAXIFS('WBS Plan'!$K7:K99,'WBS Plan'!$D7:D99,[Workstream],'WBS Plan'!$G7:G99,"<>Summary")
Planned finish = MAX(K5:[Planned finish, row above])

## Gates
Gates and Milestones
Dates and status pull from 'WBS Plan'. A gate passes only when every exit criterion has evidence.
Gate | WBS | Planned date | Status | Days before Microsoft end date | Exit criteria | Evidence required | Decision owner
G1 Scope agreed | 1.5 | 2026-10-23 | Not started | 128 | Impact assessment signed; deployment model chosen; must-do vs Phase 2 scope and budget approved; delivery team booked | Signed impact assessment, scope statement, budget approval | Sponsor
G2 Design signed off | 1.6 | 2026-11-13 | Not started | 107 | Solution design and configuration workbook signed by service ops, project accounting and controller; data mapping approved; cutover strategy agreed; licenses ordered | Signed design, mapping spec, license PO | Sponsor / Controller
G3 Build complete | 1.7 | 2026-12-18 | Not started | 72 | New integration enabled in sandbox; critical customizations refactored and unit tested; mock load 1 reconciled; critical reports rebuilt | Unit test log, mock 1 reconciliation, report list | Program Manager
G4 Go / no-go | 1.8 | 2027-02-03 | Not started | 25 | UAT signed; no open critical or high defects; mock 3 reconciled; cutover rehearsal within window; users trained; production ready | UAT sign-off, defect log, rehearsal report, readiness results | Sponsor
Go-live | 8.8 | 2027-02-08 | Not started | 20 | Legacy uninstalled in production; new integration enabled; smoke test passed; first postings reconciled | Cutover checklist, reconciliation | Sponsor
G5 Live and stable | 1.9 | 2027-02-26 | Not started | 2 | Two weeks of clean daily reconciliations; no critical defects; legacy components removed; Phase 2 backlog agreed | Hypercare exit report | Sponsor
Days before end date turns red below 14: a gate that close to February 28 leaves no room for a slip.
Formulas:
Planned date = INDEX('WBS Plan'!$J7:J99,MATCH([WBS],'WBS Plan'!$B7:B99,0))

## Estimator
Estimation Matrix and Complexity Calculator
Rough mid-market estimates, not quotes. Blue/yellow cells are editable assumptions.
Assumptions
Go-live target used for latest-start calculation | 2027-02-12 | Two weeks of buffer before Feb 28, 2027.
Holiday freeze (weeks) | 2 | Weeks lost to the Dec 21 - Jan 1 freeze.
As-of date | 2026-09-28 | From Settings.
'Start within' warning window (days) | 21 | Cells whose latest start falls inside this window turn amber.
Matrix inputs (working weeks to go-live, excluding holiday freeze and hypercare)
Data complexity | Customization complexity | Weeks (low) | Weeks (high) | Latest start (Monday) | Status | Key
Low | Low | 8 | 10 | 2026-11-16 | Comfortable | Low¦Low
Low | Medium | 10 | 12 | 2026-11-02 | Comfortable | Low¦Medium
Low | High | 12 | 14 | 2026-10-19 | Start within 3 weeks | Low¦High
Medium | Low | 10 | 12 | 2026-11-02 | Comfortable | Medium¦Low
Medium | Medium | 14 | 16 | 2026-10-05 | Start within 3 weeks | Medium¦Medium
Medium | High | 16 | 18 | 2026-09-21 | Latest start has passed | Medium¦High
High | Low | 12 | 14 | 2026-10-19 | Start within 3 weeks | High¦Low
High | Medium | 16 | 18 | 2026-09-21 | Latest start has passed | High¦Medium
High | High | 18 | 22 | 2026-08-24 | Latest start has passed | High¦High
Matrix view
Customization and integration complexity
| Low | Medium | High
Data: High | 12-14 weeks start by Oct 19 Start within 3 weeks | 16-18 weeks start by Sep 21 Latest start has passed | 18-22 weeks start by Aug 24 Latest start has passed
Data: Medium | 10-12 weeks start by Nov 2 Comfortable | 14-16 weeks start by Oct 5 Start within 3 weeks | 16-18 weeks start by Sep 21 Latest start has passed
Data: Low | 8-10 weeks start by Nov 16 Comfortable | 10-12 weeks start by Nov 2 Comfortable | 12-14 weeks start by Oct 19 Start within 3 weeks
Your organization: score each factor (Low / Medium / High)
Example values are pre-filled; replace them with your own. Level = highest level reached by two or more factors.
Dimension | Factor | Low | Medium | High | Your rating
Data | Legal entities using Field Service | 1 | 2-3 | 4 or more | Medium
Data | Open work orders expected at cutover | Under 200 | 200-1,000 | Over 1,000 | Medium
Data | Inventory on work orders | Services / non-stocked only | Some stocked items | Serialized or batch-tracked | Low
Data | Currencies on work orders | 1 | 2 | 3 or more | Low
Data | Master data quality | Clean | Some clean-up | Duplicates and gaps | Medium
Customization | Custom dual-write maps or fields on work order tables | None | 1-5 | 6 or more | Medium
Customization | Plugins, flows and scripts on work order transactions | Under 5 | 5-15 | Over 15 | Medium
Customization | Downstream systems using work order financials | None | 1-2 | 3 or more | Low
Customization | Reports built on legacy journals or subprojects | Under 5 | 5-15 | Over 15 | Medium
Customization | ISV solutions touching work orders | None | 1 | 2 or more | Low
Result
Data complexity level | Medium
Customization complexity level | Medium
Estimated working weeks to go-live | 14-16 weeks
Latest safe start (Monday) | 2026-10-05
Status | Start within 3 weeks
Thresholds and week ranges are rules of thumb from mid-market Dynamics 365 programs, not Microsoft guidance.
Formulas:
Latest start (Monday) = C5-([Weeks (high)]+C6)*7-WEEKDAY(C5-([Weeks (high)]+C6)*7,3)

## Self-Check
Twelve-Question Transition Self-Assessment
Rate each question Green / Amber / Red. 18-24 = on track, 10-17 = at risk, under 10 = act this week.
# | Question | Green (2) | Amber (1) | Red (0) | Your rating | Score
1 | Do you have an executive sponsor and budget? | Named sponsor, approved budget | Sponsor named, budget pending | Neither
2 | Is every dual-write map, flow, plugin and report touching work orders inventoried? | Documented and validated | Partly known | Unknown
3 | Have you chosen a deployment model (with or without the Project Operations app)? | Decided and documented | Under evaluation | Not discussed
4 | Are Project Operations and Power Automate licenses for the installing user confirmed? | Purchased | Quote requested | Not considered
5 | Do you have a sandbox linked to a recent copy of production F&O on the required versions? | Ready | Exists, versions unchecked | None
6 | Have customizations been assessed against the new tables (material usage logs, project actuals)? | Assessed and sized | Partly | Not assessed
7 | Is the mapping of work orders to projects and contract lines designed? | Signed off | Draft | Not started
8 | Have you decided on MUL auto-approval and the price/cost source? | Decided | Discussed | Unknown
9 | Do you have a cutover strategy for open work orders? | Decided | Discussed | Not considered
10 | Are impacted reports and downstream integrations listed with owners? | Listed with owners | Partial list | Not known
11 | Are test and training plans scheduled with named business testers? | Scheduled | Draft | None
12 | Is a delivery team with Field Service, Project Operations and F&O skills booked through March 2027? | Booked | In discussion | None
| Total score (out of 24) |  |  |  |  | 0
| Questions answered |  |  |  |  | 0
| Result |  |  |  |  | Answer all 12 questions

## RAID
RAID Log (Risks, Assumptions, Issues, Dependencies)
Pre-filled with the common risks from the article; likelihood and impact are example ratings (1-5) to replace.
ID | Type | Workstream | Description | Likelihood (1-5) | Impact (1-5) | Score | Rating | Mitigation / action | Owner | Due | Status
R01 | Risk | WS8 Cutover, Hypercare & Decommission | No side-by-side running: legacy must be uninstalled before the new integration is enabled | 4 | 5 | 20 | High | Rehearse cutover in sandbox; keep a separate sandbox for legacy support until go-live | Cutover Manager | 2027-01-29 | Open
R02 | Risk | WS3 Environments, Licensing & Security | Rebuilt sandboxes cannot install the legacy integration (toggle removed since FS 8.8.139.398) | 3 | 3 | 9 | Medium | Protect current test environment; refresh by copying production, not rebuilding | Platform Admin | 2026-10-09 | Open
R03 | Risk | WS1 Program Management & Governance | Thanksgiving, holiday freeze and year-end close remove 4-6 working weeks of finance and IT time | 5 | 4 | 20 | High | Book testers for Jan 18-29; schedule UAT after year-end close | Program Manager | 2026-10-16 | Open
R04 | Risk | WS3 Environments, Licensing & Security | License procurement delay (Project Operations, Power Automate for recurring flow) | 3 | 4 | 12 | Medium | Decide deployment model early; request quotes by Oct 16 | Platform Admin | 2026-10-16 | Open
R05 | Risk | WS3 Environments, Licensing & Security | Version prerequisites (FS 8.8.142.0+, PO 4.162.0.0+) trigger regression testing | 3 | 3 | 9 | Medium | Check versions in all environments; include upgrade regression in SIT | Technical Lead | 2026-10-07 | Open
R06 | Risk | WS4 Integration & Technical Build | Plugins, flows, scripts and custom maps built on the legacy model stop working | 4 | 4 | 16 | High | Complete technical inventory; size keep/refactor/retire | Technical Lead | 2026-10-22 | Open
R07 | Risk | WS2 Process & Solution Design | Financial structure changes (projects, contract lines, categories, revenue rules) | 4 | 5 | 20 | High | Controller attends all design workshops and signs G2 | Controller | 2026-11-13 | Open
R08 | Risk | WS5 Data Migration & Reconciliation | Open work orders with partly posted transactions at cutover | 4 | 4 | 16 | High | Close-out campaign from Jan 11; migrate only exceptions | Service Ops Lead | 2027-02-04 | Open
R09 | Risk | WS4 Integration & Technical Build | Reports reading legacy journals or subprojects return gaps | 4 | 3 | 12 | Medium | Report inventory with owners and test cases; rebuild critical reports first | BI Developer | 2026-12-16 | Open
R10 | Risk | WS6 Testing & Quality | Integration-installed offline profiles override defaults and surprise technicians | 3 | 3 | 9 | Medium | Retest offline sync on real devices; brief technicians | Functional Consultant (FS/PO) | 2027-01-15 | Open
R11 | Risk | WS1 Program Management & Governance | Partner and consultant capacity crunch as every FS + F&O customer faces the same date | 4 | 4 | 16 | High | Book delivery team through March 2027 before November | Sponsor | 2026-10-16 | Open
A01 | Assumption | WS1 Program Management & Governance | Microsoft will not extend the February 28, 2027 end date |  |  |  |  | Plan without an extension; recheck the deprecations page monthly | Program Manager |  | Open
D01 | Dependency | WS3 Environments, Licensing & Security | Microsoft Field Service / Project Operations updates may change prerequisites |  |  |  |  | Recheck Microsoft Learn setup page before build and before cutover | Solution Architect |  | Open